[bookmark: _Toc10550855][bookmark: _GoBack]Roadmap template containi	ng Actions, specific tasks, stakeholders and priorities for the session on Data generation and storage 
The tables hereafter describes the actions identified using the Need Assessment and the specific tasks, priorities and timelines to be performed in order to achieve objectives identified during the roadmap assessment. They list the lead and supporting agencies involved in their implementation, as well the implementation timeframe.


1. Data generation and storage
	Action
	Specific Tasks
	Suggested Lead Stakeholder
	Suggested Specific Supporting Stakeholders
	Prio.
	Timeline

	Handbook/Portal/
Platform
of best practice 
(= minimum requirements) covering all aspects of exposure science
	Start with mapping what is there regarding best-practices and data protection (e.g. templates from universities and national authorities) 

mapping of existing data bases
 first task for WG on data repositories?
	☐ European Agency
☐ European Commission
☒ National Authority
☐ Industry (association)
☒ Academia
☐ Scientific Society
☐ Other

	
	☒ H
☐ M
☐ L

	☒ 2020-2022
☐ 2022-2024
☐ 2024-2026
☐ 2026-2028
☐ 2028-2030


	Handbook/Portal/
Platform
of best practice
	Data collection and reporting standards for exposure data for chemicals: Minimum standards format for data reporting (LOD, LOQ) Common formats for contextual information, controlled vocabularies 

Define a base template for different topics: food, occupational, etc), OECD templates is not sufficient 

Use common European identifiers for substances, e.g. INCHI-key (CAS numbers don’t work)
	☒ European Agency
☒ European Commission
☒ National Authority
☒ Industry (association)
☒ Academia
☒ Scientific Society
☐ Other

	NORMAN network
	☒ H
☐ M
☐ L

	☒ 2020-2022
☒ 2022-2024
☐ 2024-2026
☐ 2026-2028
☐ 2028-2030


	Handbook/Portal/
Platform
of best practice
	Work towards an ISO standard for exposure data reporting

	☐ European Agency
☐ European Commission
☐ National Authority
☐ Industry (association)
☐ Academia
☐ Scientific Society
☐ Other

	ISO
	☐ H
☒ M
☐ L

	☐ 2020-2022
☐ 2022-2024
☒ 2024-2026
☒ 2026-2028
☐ 2028-2030


	Handbook/Portal/
Platform
of best practice
	Develop quality rating scheme (Q-factors like in ConsExpo fact sheets?)
(but: first have the standards for reporting)

	☐ European Agency
☐ European Commission
☒ National Authority
☒ Industry (association)
☒ Academia
☒ Scientific Society
☐ Other

	
	☒ H
☐ M
☐ L

	☐ 2020-2022
☒ 2022-2024
☒ 2024-2026
☐ 2026-2028
☐ 2028-2030


	Handbook/Portal/
Platform
of best practice
	Standards also needed for other stressors (noise, radiation etc.)

	☐ European Agency
☐ European Commission
☐ National Authority
☐ Industry (association)
☐ Academia
☐ Scientific Society
☐ Other

	
	☒ H
☐ M
☐ L

	☐ 2020-2022
☐ 2022-2024
☒ 2024-2026
☒ 2026-2028
☐ 2028-2030


	Handbook/Portal/
Platform
of best practice
	Guidance on how to deal with data protection issues/consent etc. in exposure science 

guidance available from universities how to deal with GDPR
	☒ European Agency
☒ European Commission
☒ National Authority
☐ Industry (association)
☒ Academia
☒ Scientific Society
☐ Other

	DG JUST, HBM4EU, IPCHEM,

Invite talk for next meeting (e.g. Marlon Domingus, Nijmegen Uni?)

	☒ H
☐ M
☐ L

	☒ 2020-2022
☐ 2022-2024
☐ 2024-2026
☐ 2026-2028
☐ 2028-2030


	Handbook/Portal/
Platform
of best practice 
	Define desirable common requirements for IT infrastructure for data exchange and storage (compatible and suitable hardware),

Find out what can we learn from ELIXIR?
	☒ European Agency
☐ European Commission
☒ National Authority
☒ Industry (association)
☒ Academia
☐ Scientific Society
☐ Other

	
	☐ H
☒ M
☐ L

	☐ 2020-2022
☒ 2022-2024
☒ 2024-2026
☐ 2026-2028
☐ 2028-2030


	Stimulation of data sharing 

	Develop suitable “contracts”, defining ownership, restrictions (e.g. which users), e.g. based on standard creative commons license, 

Put a link to contracts from previous contracts and general templates on the website of ISES-Europe

Provide webinars and training

	☒ European Agency
☐ European Commission
☒ National Authority
☒ Industry (association)
☒ Academia
☒ Scientific Society
☐ Other

	
	☒ H
☒ M
☐ L

	☒ 2020-2022
☒ 2022-2024
☒ 2024-2026
☐ 2026-2028
☐ 2028-2030


	Networking across exposure science disciplines and regions

	
	☐ European Agency
☐ European Commission
☐ National Authority
☐ Industry (association)
☐ Academia
☐ Scientific Society
☐ Other

	
	☐ H
☐ M
☐ L

	☐ 2020-2022
☐ 2022-2024
☐ 2024-2026
☐ 2026-2028
☐ 2028-2030


	Data base for exposure factors in Europe
	Develop a current data base building on national handbooks, JRC ExpoFacts or ConsExpo

· tasks discussed tomorrow in WG on repositories
	☐ European Agency
☐ European Commission
☐ National Authority
☐ Industry (association)
☐ Academia
☐ Scientific Society
☐ Other

	
	☐ H
☐ M
☐ L

	☐ 2020-2022
☐ 2022-2024
☐ 2024-2026
☐ 2026-2028
☐ 2028-2030




