Roadmap template containi	ng Actions, specific tasks, stakeholders and priorities for the session on Data generation and storage

The tables hereafter describes the actions identified using the Need Assessment and the specific tasks, priorities and timelines to be performed in order to achieve objectives identified during the roadmap assessment. They list the lead and supporting agencies involved in their implementation, as well the implementation timeframe.

- Data generation and storage

| Action | Specific Tasks | Suggested Lead Stakeholder | Suggested Specific Supporting Stakeholders | Prio. | Timeline |
| --- | --- | --- | --- | --- | --- |
| Handbook/Portal/ Platform of best practice (= minimum requirements) covering all aspects of exposure science | Start with mapping what is there regarding best-practices and data protection (e.g. templates from universities and national authorities) mapping of existing data bases first task for WG on data repositories? | ☐ European Agency ☐ European Commission ☒ National Authority ☐ Industry (association) ☒ Academia ☐ Scientific Society ☐ Other |  | ☒ H ☐ M ☐ L | ☒ 2020-2022 ☐ 2022-2024 ☐ 2024-2026 ☐ 2026-2028 ☐ 2028-2030 |
| Handbook/Portal/ Platform of best practice | Data collection and reporting standards for exposure data for chemicals: Minimum standards format for data reporting (LOD, LOQ) Common formats for contextual information, controlled vocabularies Define a base template for different topics: food, occupational, etc), OECD templates is not sufficient Use common European identifiers for substances, e.g. INCHI-key (CAS numbers don’t work) | ☒ European Agency ☒ European Commission ☒ National Authority ☒ Industry (association) ☒ Academia ☒ Scientific Society ☐ Other | NORMAN network | ☒ H ☐ M ☐ L | ☒ 2020-2022 ☒ 2022-2024 ☐ 2024-2026 ☐ 2026-2028 ☐ 2028-2030 |
| Handbook/Portal/ Platform of best practice | Work towards an ISO standard for exposure data reporting | ☐ European Agency ☐ European Commission ☐ National Authority ☐ Industry (association) ☐ Academia ☐ Scientific Society ☐ Other | ISO | ☐ H ☒ M ☐ L | ☐ 2020-2022 ☐ 2022-2024 ☒ 2024-2026 ☒ 2026-2028 ☐ 2028-2030 |
| Handbook/Portal/ Platform of best practice | Develop quality rating scheme (Q-factors like in ConsExpo fact sheets?) (but: first have the standards for reporting) | ☐ European Agency ☐ European Commission ☒ National Authority ☒ Industry (association) ☒ Academia ☒ Scientific Society ☐ Other |  | ☒ H ☐ M ☐ L | ☐ 2020-2022 ☒ 2022-2024 ☒ 2024-2026 ☐ 2026-2028 ☐ 2028-2030 |
| Handbook/Portal/ Platform of best practice | Standards also needed for other stressors (noise, radiation etc.) | ☐ European Agency ☐ European Commission ☐ National Authority ☐ Industry (association) ☐ Academia ☐ Scientific Society ☐ Other |  | ☒ H ☐ M ☐ L | ☐ 2020-2022 ☐ 2022-2024 ☒ 2024-2026 ☒ 2026-2028 ☐ 2028-2030 |
| Handbook/Portal/ Platform of best practice | Guidance on how to deal with data protection issues/consent etc. in exposure science guidance available from universities how to deal with GDPR | ☒ European Agency ☒ European Commission ☒ National Authority ☐ Industry (association) ☒ Academia ☒ Scientific Society ☐ Other | DG JUST, HBM4EU, IPCHEM, Invite talk for next meeting (e.g. Marlon Domingus, Nijmegen Uni?) | ☒ H ☐ M ☐ L | ☒ 2020-2022 ☐ 2022-2024 ☐ 2024-2026 ☐ 2026-2028 ☐ 2028-2030 |
| Handbook/Portal/ Platform of best practice | Define desirable common requirements for IT infrastructure for data exchange and storage (compatible and suitable hardware), Find out what can we learn from ELIXIR? | ☒ European Agency ☐ European Commission ☒ National Authority ☒ Industry (association) ☒ Academia ☐ Scientific Society ☐ Other |  | ☐ H ☒ M ☐ L | ☐ 2020-2022 ☒ 2022-2024 ☒ 2024-2026 ☐ 2026-2028 ☐ 2028-2030 |
| Stimulation of data sharing | Develop suitable “contracts”, defining ownership, restrictions (e.g. which users), e.g. based on standard creative commons license, Put a link to contracts from previous contracts and general templates on the website of ISES-Europe Provide webinars and training | ☒ European Agency ☐ European Commission ☒ National Authority ☒ Industry (association) ☒ Academia ☒ Scientific Society ☐ Other |  | ☒ H ☒ M ☐ L | ☒ 2020-2022 ☒ 2022-2024 ☒ 2024-2026 ☐ 2026-2028 ☐ 2028-2030 |
| Networking across exposure science disciplines and regions |  | ☐ European Agency ☐ European Commission ☐ National Authority ☐ Industry (association) ☐ Academia ☐ Scientific Society ☐ Other |  | ☐ H ☐ M ☐ L | ☐ 2020-2022 ☐ 2022-2024 ☐ 2024-2026 ☐ 2026-2028 ☐ 2028-2030 |
| Data base for exposure factors in Europe | Develop a current data base building on national handbooks, JRC ExpoFacts or ConsExpo - tasks discussed tomorrow in WG on repositories | ☐ European Agency ☐ European Commission ☐ National Authority ☐ Industry (association) ☐ Academia ☐ Scientific Society ☐ Other |  | ☐ H ☐ M ☐ L | ☐ 2020-2022 ☐ 2022-2024 ☐ 2024-2026 ☐ 2026-2028 ☐ 2028-2030 |