Working Group on Data repositories and Analytics

| Action | Specific Tasks | Suggested Lead Stakeholder (not necessarily workshop participants). | Suggested Specific Supporting Stakeholders(not necessarily workshop participants) | Priority | Timeline |
| --- | --- | --- | --- | --- | --- |
| Setup an inventory of existing data sources, models and already undertaken case studies which have been used in EU and beyond linking environmental exposure and health data with specific health outcomes |  | ☐ European Agency ☒ EC JRC ☐ National Authority ☐ Industry (association) ☐ Academia |  | ☒ H ☐ M ☐ L | ☒ 2020-2022 ☐ 2022-2024 ☐ 2024-2026 |
| Identify critical gaps in terms of data, methods, models and barriers in their use (e.g. constraints relating to geographical level of coverage and detail, time window, semantic and technical interoperability among distributed data and information platforms) | Dedicated working group with gap assessment in regulation/other fields? | ☐ European Agency ☒ European Commission ☒ National Authority ☐ Industry (association) ☐ Academia |  | ☒ H ☐ M ☐ L | ☐ 2020-2022 ☒ 2022-2024 ☐ 2024-2026 |
| Prioritise actions to fill in the identified critical gaps within respective timelines (short, medium, long-term) for defining and undertaking new case studies of high relevance for EU and MS policies and for advancing science |  | ☐ European Agency ☐ European Commission ☐ National Authority ☐ Industry (association) ☐ Academia |  | ☐ H ☒ M ☐ L | ☐ 2020-2022 ☐ 2022-2024 ☒ 2024-2026 |
| Map the state of the art exploitation of technologies related to text mining and analysis, machine learning, artificial intelligence, interconnection of big data domains, visualisation tools with the aim of bridging the gap from data to knowledge |  | ☐ European Agency ☒ European Commission ☐ National Authority ☐ Industry (association) ☐ Academia |  | ☒ H ☐ M ☐ L | ☒ 2020-2022 ☐ 2022-2024 ☐ 2024-2026 |
| Promote harmonisation of terms, controlled vocabularies, templates for data and metadata documentation and reporting, standardisation of data collection methods and development of indicators for data quality and comparability across exposure relevant policy domains and regulations | Meta data and tiered information templates tailored toward specific contexts (i.e. give overview of specific requirements per context and then this could be added to test guidelines and standard protocols to be shared at fairsharing.org) – link up with science Europe (funding mechanism), itemization | ☐ European Agency ☐ European Commission ☐ National Authority ☐ Industry (association) ☐ Academia |  | ☒ H ☐ M ☐ L | ☐ 2020-2022 ☒ 2022-2024 ☐ 2024-2026 |
| Establish common principles and framework for data sharing and use/re-use among stakeholders while respecting protection of intellectual property rights and personal (sensitive) data |  | ☒ European Agency ☐ European Commission ☐ National Authority ☐ Industry (association) ☐ Academia | Norman network | ☒ H ☐ M ☐ L | ☒ 2020-2022 ☒ 2022-2024 ☒ 2024-2026 |
| Pooling together and sharing best practices for data integration and interpretation, standardised and harmonised datasets, tools, models and performance indicators that are used in policy making, exposure and health risk assessments, surveillance and monitoring activities, evaluation of intervention measures and health information systems |  | ☐ European Agency ☒ European Commission ☐ National Authority ☐ Industry (association) ☐ Academia | DG RTD Norman network | ☐ H ☒ M ☐ L | ☐ 2020-2022 ☐ 2022-2024 ☒ 2024-2026 |
| Setup a stakeholders community for data repositories and analytics |  | ☐ European Agency ☐ European Commission ☐ National Authority ☒ ISES Europe (Jos) ☐ Academia |  | ☐ H ☒ M ☐ L | ☒ 2020-2022 ☐ 2022-2024 ☐ 2024-2026 |
| A working group or a project on “A data base for exposure factors in Europe” (building on national handbooks, JRC ExpoFacts or ConsExpo Fact sheets) | Revitalisation of European exposure factor collection including: - Definition of needs, hosting and quality requirements - Use of existing formats, like ConsExpo fact sheets or OECD harmonised template OHT301 - Setting up a Committee that derives standard default values in specific areas Preparation of and requesting funding for a COST action project | ☐ European Agency ☐ European Commission ☒ National Authority ☐ Industry (association) ☐ Academia | UBA? N vGoetz org.? | ☐ H ☒ M ☐ L | ☐ 2020-2022 ☐ 2022-2024 ☐ 2024-2026 |
| Setting up Working Group on “Interoperability” | - Data sharing principles/data provision incentives - IT technologies, distributed systems, platforms | ☐ European Agency ☒ EC JRC ☐ National Authority ☐ Industry (association) ☐ Academia |  | ☐ H ☒ M ☐ L | ☐ 2020-2022 ☐ 2022-2024 ☒ 2024-2026 |